## Sheet1
ID | TAG | Estado | Nº Oferta | Nº Pedido | PO | Posición | Subposición | Tipo | Tamaño Línea | Rating | Facing | Schedule | Material Brida | Tipo Brida | Material Tubo | Tamaño Tomas (Nº x Brida) | Material Elemento | Tipo Placa | Espesor Placa | Estándar Placa | Material Junta | Material Tornillería | Con. Válvula | Material Cuerpo Vlv. | Nº Saltos | Pipe Spec. | Peso Aprox. (kg) | Long. Aprox. (mm) | NACE | Notas Oferta | Cambios Comercial | Fecha Contractual | Ø Orif. (mm) | Ø D/V (mm) | Cambios Técnicos | Notas Técnicas | Nº Doc. EIPSA Cálculo | Estado Cálculo | Fecha Estado Cálculo | Nº Doc. EIPSA Plano | Estado Plano | Fecha Estado Plano | Orden de Compra | Fecha Orden Compra | Notas Orden Compra | Plano Dimensional | Plano OF | Fecha OF | Notas Equipo | Colada Placa | Cert. Placa | Colada Brida | Cert. Brida | Nº Tapones | Tamaño Tomas | Nº Tomas x Brida | RTJ Porta Material | RTJ Espesor | RTJ Dim | Ø Ext. Placa (mm) | Mango | Tamaño Espárragos | Cantidad Espárragos | Tamaño Extractor | Cantidad Extractor | Estado Fabricación | Inspección | Fecha Inspección | Envío RN | Fecha RN | Fecha PMI | Fecha PH1 | Fecha PH2 | Fecha LP | Fecha Dureza | Fecha Verif. Dim. | Fecha Verif. OF | Fotos | Fotos 2
id_tag_flow | tag | tag_state | num_offer | num_order | num_po | position | subposition | item_type | line_size | rating | facing | schedule | flange_material | flange_type | tube_material | tapping_num_size | element_material | plate_type | plate_thk | plate_std | gasket_material | bolts_nuts_material | valve_conn | valve_material_body | stages_number | pipe_spec | aprox_weight | aprox_length | nace | offer_notes | commercial_changes | contractual_date | orif_diam | dv_diam | technical_changes | technical_notes | calc_num_doc_eipsa | calc_state | calc_state_date | dwg_num_doc_eipsa | dwg_state | dwg_state_date | purchase_order | purchase_order_date | purchase_order_notes | dim_drawing | of_drawing | of_date | notes_equipment | heat_number_plate | cert_plate | heat_number_flange | cert_flange | plug_number | tapping_size | tapping_number | rtj_porta_material | rtj_thickness | rtj_dim | plate_ext_diam | handle | bolts_size | bolts_quantity | extractor_size | extractor_quantity | fab_state | inspection | irc_date | rn_delivery | rn_date | pmi_date | ph1_date | ph2_date | lp_date | hard_date | final_verif_dim_date | final_verif_of_eq_date | tag_images | tag_images2
3647 | 171FE -6701P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 124 | P | 8" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 3 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-171-S08-01 | OF-03/05 |  |  | 2VTJ |  |  |  | 0 |  | 0 |  |  |  | 308 | 100x30x3 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_090152592_HDR_AE.jpg
3648 | 171FE -6703P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 125 | P | 8" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 3 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-01 | OF-03/05 |  |  | 2VTJ |  |  |  | 0 |  | 0 |  |  |  | 308 | 100x30x3 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_090213576_HDR_AE.jpg
3649 | 171FE -7201P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 126 | P | 8" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 3 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-01 | OF-03/05 |  |  | 2VTJ |  |  |  | 0 |  | 0 |  |  |  | 308 | 100x30x3 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_090236457_AE.jpg
3650 | 171FE -7203P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 127 | P | 8" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 3 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-01 | OF-03/05 |  |  | 2VTJ |  |  |  | 0 |  | 0 |  |  |  | 308 | 100x30x3 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_090300336_AE.jpg
3651 | 171FE -7205P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 128 | P | 16" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 9,5 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-02 | OF-04/05 |  |  | 332363 |  |  |  | 0 |  | 0 |  |  |  | 540 | 150x45x6 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 11/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250311_113132719_AE.jpg
3652 | 171FE -7207P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 129 | P | 16" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 9,5 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-02 | OF-04/05 |  |  | 332363 |  |  |  | 0 |  | 0 |  |  |  | 540 | 150x45x6 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 11/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250311_113053517_HDR_AE.jpg
3653 | 171FE -7209P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 130 | P | 16" | 300 | RF | 20 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 9,5 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-02 | OF-04/05 |  |  | 332363 |  |  |  | 0 |  | 0 |  |  |  | 540 | 150x45x6 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 11/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250311_113116281_AE.jpg
3654 | 175FE -311P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 131 | P | 4" | 300 | RF | 80 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 9,5 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-02 | OF-02/05 |  |  | W5KV |  |  |  | 0 |  | 0 |  |  |  | 181 | 100x30x6 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_085929657_HDR_AE.jpg
3655 | 175FE -703P_ | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 1 | 132 | P | 3" | 300 | RF | 40 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 9,5 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-01 | OF-01/05 |  |  | Z8WL |  |  |  | 0 |  | 0 |  |  |  |  | Sin datos para 3" 300 RF EIP 9,5 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 18/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250318_090006476_HDR_AE.jpg
3656 | 175RO -302P | PURCHASED | P-23/044-S08 | P-23/044-S08 | 1037010910-08 | 3 | 154 | RO | 2" | 150 | RF | 160 | N/A | N/A | N/A | N/A | A240 TP 316/316L | SQE | 3 | EIP | N/A | N/A | [6 empty] | NO | [16 empty] | 23/044-175-S08-O-01 | OF-05/05 |  |  | 3MCK |  |  |  | 0 |  | 0 |  |  |  | 105 | 100x30x3 |  | 0 |  | 0 | [5 empty] | 06/03/2025 | [5 empty] | 21/03/2025 | //SRVAD01/base de datos de pedidos/Año 2023/2023 Pedidos/P-23-044 - S08 - S09R - TR - QATAR NFE PACKAGE 3 - CAUDAL/Z-Fotos Verificacion/IMG_20250321_084858408_AE.jpg